## BACKLOG
THE APPLICATION DEVELOPMENT PROJECT TOPIC PRODUCT BACKLOG
STT | Function Name | Feature | Complexity | Planned Code Iteration | In-charge Roll Number | In-charge Full Name | Actual Code Iteration | Time: Begin | Time: Deadline | Time: Resit | Note
1 | Login | Login | Simple | Iteration 1 | CE180749 | Kiều Hoàng Mạnh Khang | Iteration 1 | 2025-05-22 | 2025-05-22 | 2025-06-15 | Done
2 | Logout | Logout | Medium | Iteration 2 | CE180749 | Kiều Hoàng Mạnh Khang | Iteration 3 | 2025-05-23 | 2025-05-23
3 | Register With Email | Manage Register | Simple | Iteration 2 | CE180749 | Kiều Hoàng Mạnh Khang | Iteration 3 | 2025-05-24 | 2025-05-24
4 | Register With Google | Manage Register | Simple | Iteration 2 | CE181988 | Kiều Hoàng Mạnh Khang | Iteration 3 | 2025-05-25 | 2025-05-25
5 | Register With Facebook | Manage Register | Simple | Iteration 2 | CE181988 | Kiều Hoàng Mạnh Khang | Iteration 3 | 2025-05-26 | 2025-05-26
6 | View Review Room | Manage Rooms | Simple | Iteration 1 | CE181988 | Kiều Hoàng Mạnh Khang | Iteration 1 | 2025-05-27 | 2025-05-27 | 2025-06-15 | Done
9 | View Vouchers | Manage Vouchers | Simple | Iteration 1 | CE180441 | Dương Đinh Thế Vinh | Iteration 1 | 2025-05-30 | 2025-06-15 | 2025-06-16 | Done
10 | View Laundry | Manage Services | Simple | Iteration 3 | CE180441 | Đỗ Đăng Khoa | Iteration 3 | 2025-05-25 | 2025-05-26
11 | View all News | Manage News | Simple | Iteration 1 | CE180441 | Đỗ Đăng Khoa | Iteration 1 | 2025-06-01 | 2025-06-01 | 2025-06-15 | Done
12 | View News Detail | Manage News | Simple | Iteration 1 | CE180441 | Đỗ Đăng Khoa | Iteration 1 | 2025-06-02 | 2025-06-02 | 2025-06-15 | Done
13 | Save Vouchers | Manage Vouchers | Simple | Iteration 1 | CE180441 | Dương Đinh Thế Vinh | Iteration 1 | 2025-06-14 | 2025-06-16 | 2025-06-16 | Done
14 | Edit Profile | Manage Profile | Simple | Iteration 1 | CE181988 | Đỗ Đăng Khoa | Iteration 1 | 2025-06-04 | 2025-06-04 | 2025-06-15 | Done
15 | View Profile | Manage Profile | Simple | Iteration 1 | CE181988 | Đỗ Đăng Khoa | Iteration 1 | 2025-06-05 | 2025-06-05 | 2025-06-15 | Done
16 | Change Password For Customer | Manage Profile | Medium | Iteration 1 | CE181988 | Đỗ Đăng Khoa | Iteration 3 | 2025-06-27 | 2025-06-29
17 | View Last Login | Manage Profile | Simple | Iteration 1 | CE181988 | Đỗ Đăng Khoa | Iteration 1 | 2025-06-07 | 2025-06-08 | 2025-06-15 | Done
18 | Forgot Password | Manage Profile | Medium | Iteration 3 | CE181988 | Đỗ Đăng Khoa | Iteration 3 | 2025-06-23 | 2025-06-25
19 | Booking Room | Manage Bookings | Simple | Iteration 3 | CE181988 | Đỗ Đăng Khoa | Iteration 3 | 2025-06-23 | 2025-06-25
20 | View Booking History | Manage Bookings | Simple | Iteration 3 | CE181988 | Đỗ Đăng Khoa | Iteration 3 | 2025-06-16 | 2025-06-18
21 | Payment | Manage Payment | Medium | Iteration 3 | CE180749 | Kiều Hoàng Mạnh Khang | Iteration 3 | 2025-06-29 | 2025-06-30
22 | View Notifications Detail From Admin | Manage Notifications | Simple | Iteration 3 | CE180749 | Kiều Hoàng Mạnh Khang | Iteration 3 | 2025-06-28 | 2025-06-29
23 | View Notifications From Admin | Manage Notifications | Simple | Iteration 2 | CE181640 | Kiều Hoàng Mạnh Khang | Iteration 3 | 2025-06-18 | 2025-06-23
24 | View Bookings | Manage Bookings | Simple | Iteration 2 | CE181640 | Lê Huỳnh Nhựt Khanh | Iteration 3 | 2025-06-18 | 2025-06-23
25 | View Booking Detail | Manage Bookings | Simple | Iteration 2 | CE181640 | Lê Huỳnh Nhựt Khanh | Iteration 3 | 2025-06-18 | 2025-06-23
26 | Confirm Booking | Manage Bookings | Medium | Iteration 2 | CE181640 | Lê Huỳnh Nhựt Khanh | Iteration 3 | 2025-06-18 | 2025-06-23
27 | Search Customer Booking | Manage Bookings | Simple | Iteration 3 | CE180749 | Kiều Hoàng Mạnh Khang | Iteration 3 | 2025-06-28 | 2025-06-29
28 | View CheckIn / CheckOut Room Detail | Manage Check-In/Out | Simple | Iteration 3 | CE181640 | Lê Huỳnh Nhựt Khanh | Iteration 3 | 2025-06-20 | 2025-06-25
29 | View CheckIn / CheckOut Room | Manage Check-In/Out | Simple | Iteration 3 | CE181640 | Lê Huỳnh Nhựt Khanh | Iteration 3 | 2025-06-20 | 2025-06-25
30 | View Notification Detail From Admin | Manage Notifications | Simple | Iteration 2 | CE180749 | Kiều Hoàng Mạnh Khang | Iteration 3 | 2025-06-20 | 2025-06-20
| Send Message | Manage Messaging | Simple | Iteration 2 | CE180749 | Kiều Hoàng Mạnh Khang | Iteration 3
| View All Messaging History | Manage Messaging | Simple | Iteration 2 | CE180749 | Kiều Hoàng Mạnh Khang | Iteration 3
31 | View All Notifications From Admin | Manage Notifications | Simple | Iteration 2 | CE180749 | Kiều Hoàng Mạnh Khang | Iteration 3 | 2025-06-21 | 2025-06-21
32 | Send Message With Customer | Manage Customer Suport | Medium | Iteration 2 | CE180749 | Kiều Hoàng Mạnh Khang | Iteration 3 | 2025-06-27 | 2025-06-29
| View Messages With Customer | Manage Customer Suport | Simple | Iteration 2 | CE180749 | Kiều Hoàng Mạnh Khang | Iteration 3 | 2025-06-27 | 2025-06-29
33 | View Message With Customer Detail | Manage Customer Suport | Simple | Iteration 2 | CE180749 | Kiều Hoàng Mạnh Khang | Iteration 3 | 2025-06-27 | 2025-06-29
34 | Update Delivery Status | Manage Delivery | Simple | Iteration 3 | CE181988 | Đỗ Đăng Khoa | Iteration 3 | 2025-06-16 | 2025-06-18
35 | View All Assigned Orders | Manage Delivery | Simple | Iteration 3 | CE181988 | Đỗ Đăng Khoa | Iteration 3 | 2025-06-25 | 2025-06-25
36 | Confirm Laundry | Manage Laundry | Simple | Iteration 3 | CE181988 | Đỗ Đăng Khoa | Iteration 3 | 2025-06-26 | 2025-06-26
37 | View All Orders Laundrys | Manage Laundry | Simple | Iteration 3 | CE181988 | Đỗ Đăng Khoa | Iteration 3 | 2025-06-24 | 2025-06-25
38 | View Order Laundry Detail | Manage Laundry | Simple | Iteration 3 | CE181988 | Đỗ Đăng Khoa | Iteration 3 | 2025-06-24 | 2025-06-25
39 | Update Order Laundry Status | Manage Laundry | Simple | Iteration 3 | CE181988 | Đỗ Đăng Khoa | Iteration 3 | 2025-06-24 | 2025-06-25
40 | Confirm Cleaning Room | Manage Cleaning | Simple | Iteration 3 | CE181988 | Đỗ Đăng Khoa | Iteration 3 | 2025-06-24 | 2025-06-25
41 | View All Orders Cleanings | Manage Cleaning | Simple | Iteration 3 | CE181988 | Đỗ Đăng Khoa | Iteration 3 | 2025-06-19 | 2025-06-21
42 | View Order Cleaning Detail | Manage Cleaning | Simple | Iteration 3 | CE181988 | Đỗ Đăng Khoa | Iteration 3 | 2025-06-19 | 2025-06-21
43 | Update Order Cleaning Status | Manage Cleaning | Simple | Iteration 3 | CE181988 | Đỗ Đăng Khoa | Iteration 3 | 2025-06-19 | 2025-06-21
44 | Report Room Issues | Manage Reports | Simple | Iteration 3 | CE180441 | Lê Huỳnh Nhựt Khanh | Iteration 3 | 2025-06-22 | 2025-06-29
45 | View On-Duty Room Detail | Manage Duty | Simple | Iteration 2 | CE181640 | Lê Huỳnh Nhựt Khanh | Iteration 3 | 2025-06-20 | 2025-06-25
46 | View All On-Duty Rooms | Manage Duty | Simple | Iteration 2 | CE181640 | Kiều Hoàng Mạnh Khang | Iteration 3 | 2025-06-20 | 2025-06-25
47 | View All Customers For Dasboard | Manage Customer | Simple | Iteration 1 | CE180749 | Lê Huỳnh Nhựt Khanh | Iteration 1 | 2025-06-17 | 2025-07-07 | 2025-07-07 | Done
48 | Search Customer | Manage Customer | Simple | Iteration 1 | CE180749 | Lê Huỳnh Nhựt Khanh | Iteration 2 | 2025-06-17 | 2025-07-08
49 | Deactivated Staff | Manage Staff | Simple | Iteration 3 | CE180749 | Kiều Hoàng Mạnh Khang | Iteration 3 | 2025-06-17 | 2025-06-21
50 | View All Staff | Manage Staff | Simple | Iteration 1 | CE180749 | Kiều Hoàng Mạnh Khang | Iteration 1 | 2025-06-18 | 2025-06-22 | 2025-07-10 | Done
51 | Search Staff | Manage Staff | Simple | Iteration 3 | CE180749 | Kiều Hoàng Mạnh Khang | Iteration 3 | 2025-06-18 | 2025-06-22
52 | Create Staff | Manage Staff | Simple | Iteration 3 | CE180749 | Kiều Hoàng Mạnh Khang | Iteration 3 | 2025-06-18 | 2025-06-22
53 | Update Staff | Manage Staff | Simple | Iteration 3 | CE180749 | Kiều Hoàng Mạnh Khang | Iteration 3 | 2025-06-18 | 2025-06-22
54 | View Staff Detail | Manage Staff | Simple | Iteration 1 | CE180749 | Kiều Hoàng Mạnh Khang | Iteration 3 | 2025-06-18 | 2025-06-22
58 | View All Rooms | Manage Rooms | Simple | Iteration 1 | CE180749 | Kiều Hoàng Mạnh Khang | Iteration 1 | 2025-06-19 | 2025-06-23 | 2025-07-18 | Done
59 | View Room Detail | Manage Rooms | Simple | Iteration 1 | CE180749 | Kiều Hoàng Mạnh Khang | Iteration 1 | 2025-07-19 | 2025-06-23 | 2025-07-19 | Done
60 | Create Room | Manage Rooms | Simple | Iteration 1 | CE180749 | Kiều Hoàng Mạnh Khang | Iteration 2 | 2025-06-19 | 2025-06-23
61 | Update Room | Manage Rooms | Simple | Iteration 1 | CE180749 | Kiều Hoàng Mạnh Khang | Iteration 2 | 2025-06-19 | 2025-06-23
62 | Delete Room | Manage Rooms | Simple | Iteration 1 | CE180749 | Kiều Hoàng Mạnh Khang | Iteration 2 | 2025-06-19 | 2025-06-23
63 | Search Room | Manage Rooms | Simple | Iteration 1 | CE180749 | Kiều Hoàng Mạnh Khang | Iteration 1 | 2025-06-20 | 2025-06-24 | 2025-07-23 | Done
64 | View All Room For Admin | Manage Rooms | Simple | Iteration 2 | CE181640 | Kiều Hoàng Mạnh Khang | Iteration 3 | 2025-06-20 | 2025-06-25 |  | Done
65 | Sort Room For Dashboard | Manage Rooms | Simple | Iteration 2 | CE180749 | Kiều Hoàng Mạnh Khang | Iteration 3 | 2025-06-20 | 2025-06-25
66 | Search Booking | Manage Bookings | Simple | Iteration 2 | CE180441 | Dương Đinh Thế Vinh | Iteration 3 | 2025-06-17 | 2025-06-29
67 | View All Booking | Manage Bookings | Simple | Iteration 1 | CE180441 | Dương Đinh Thế Vinh | Iteration 1 | 2025-06-17 | 2025-06-18 | 2025-06-18 | Done
68 | View Booking Detail | Manage Bookings | Simple | Iteration 1 | CE180441 | Dương Đinh Thế Vinh | Iteration 1 | 2025-06-17 | 2025-06-18 | 2025-06-18 | Done
69 | Delete Booking | Manage Bookings | Simple | Iteration 1 | CE180441 | Dương Đinh Thế Vinh | Iteration 1 | 2025-06-17 | 2025-06-18 | 2025-06-18 | Done
70 | View All Services For Dashboard | Manage Services | Simple | Iteration 1 | CE181988 | Đỗ Đăng Khoa | Iteration 1 | 2025-06-17 | 2025-06-18 | 2025-06-26 | Done
71 | View Services | Manage Services | Simple | Iteration 1 | CE181988 | Đỗ Đăng Khoa | Iteration 1 | 2025-06-17 | 2025-06-19 | 2025-06-26 | Done
72 | Create ServicesService | Manage Services | Simple | Iteration 1 | CE181988 | Đỗ Đăng Khoa | Iteration 1 | 2025-06-17 | 2025-06-19 | 2025-06-26 | Done
73 | Update ServicesService | Manage Services | Simple | Iteration 1 | CE181988 | Đỗ Đăng Khoa | Iteration 1 | 2025-06-17 | 2025-06-18 | 2025-06-26 | Done
74 | Delete ServicesService | Manage Services | Simple | Iteration 1 | CE181988 | Đỗ Đăng Khoa | Iteration 1 | 2025-06-17 | 2025-06-18 | 2025-06-26 | Done
75 | View Cleaning Room Service | Manage Services | Simple | Iteration 3 | CE181988 | Đỗ Đăng Khoa | Iteration 3 | 2025-06-20 | 2025-06-22
76 | Update Cleaning Service | Manage Services | Simple | Iteration 3 | CE181988 | Đỗ Đăng Khoa | Iteration 3 | 2025-06-20 | 2025-06-22
77 | View All Reports For Dashboard | Manage Reports | Simple | Iteration 2 | CE181640 | Lê Huỳnh Nhựt Khanh | Iteration 3 | 2025-06-24 | 2025-06-28
78 | View Report Detail | Manage Reports | Simple | Iteration 2 | CE181640 | Lê Huỳnh Nhựt Khanh | Iteration 3 | 2025-06-24 | 2025-06-28
79 | Update Report | Manage Reports | Simple | Iteration 2 | CE181640 | Lê Huỳnh Nhựt Khanh | Iteration 3 | 2025-06-23 | 2025-06-27
80 | Delete Report | Manage Reports | Simple | Iteration 2 | CE181640 | Lê Huỳnh Nhựt Khanh | Iteration 3 | 2025-06-23 | 2025-06-27
81 | Create Report | Manage Reports | Simple | Iteration 2 | CE181640 | Lê Huỳnh Nhựt Khanh | Iteration 3 | 2025-06-23 | 2025-06-27
82 | View All Notifications for Admin | Manage Notifications | Simple | Iteration 3 | CE180749 | Kiều Hoàng Mạnh Khang | Iteration 3 | 2025-06-21 | 2025-06-26
83 | Create Notification | Manage Notifications | Simple | Iteration 3 | CE180749 | Kiều Hoàng Mạnh Khang | Iteration 3 | 2025-06-21 | 2025-06-26
84 | Update Notification | Manage Notifications | Simple | Iteration 3 | CE180749 | Kiều Hoàng Mạnh Khang | Iteration 3 | 2025-06-22 | 2025-06-26
85 | View Notification Detail | Manage Notifications | Simple | Iteration 3 | CE180749 | Kiều Hoàng Mạnh Khang | Iteration 3 | 2025-06-23 | 2025-06-26
86 | Delete Notification | Manage Notifications | Simple | Iteration 3 | CE180749 | Kiều Hoàng Mạnh Khang | Iteration 3 | 2025-06-24 | 2025-06-26
87 | View All Vouchers For Admin | Manage Vouchers | Simple | Iteration 1 | CE180441 | Dương Đinh Thế Vinh | Iteration 1 | 2025-06-04 | 2025-06-07 | 2025-06-07 | Done
88 | Create Voucher | Manage Vouchers | Simple | Iteration 1 | CE180441 | Dương Đinh Thế Vinh | Iteration 1 | 2025-06-07 | 2025-06-09 | 2025-06-09 | Done
89 | View Voucher Detail | Manage Vouchers | Simple | Iteration 1 | CE180441 | Dương Đinh Thế Vinh | Iteration 1 | 2025-06-10 | 2025-06-12 | 2025-06-12 | Done
90 | Delete Voucher | Manage Vouchers | Simple | Iteration 1 | CE180441 | Dương Đinh Thế Vinh | Iteration 1 | 2025-06-12 | 2025-06-14 | 2025-06-14 | Done
91 | Update Voucher | Manage Vouchers | Simple | Iteration 1 | CE180441 | Dương Đinh Thế Vinh | Iteration 1 | 2025-06-12 | 2025-06-14 | 2025-06-14 | Done
93 | View All News for Dashboard | Manage News | Simple | Iteration 1 | CE181988 | Đỗ Đăng Khoa | Iteration 1 | 2025-06-08 | 2025-06-10 | 2025-06-15 | Done
94 | Create News | Manage News | Simple | Iteration 1 | CE181988 | Đỗ Đăng Khoa | Iteration 1 | 2025-06-08 | 2025-06-10 | 2025-06-15 | Done
95 | Update News | Manage News | Simple | Iteration 1 | CE181988 | Đỗ Đăng Khoa | Iteration 1 | 2025-06-08 | 2025-06-10 | 2025-06-15 | Done
96 | Delete News | Manage News | Simple | Iteration 1 | CE181988 | Đỗ Đăng Khoa | Iteration 1 | 2025-06-08 | 2025-06-10 | 2025-06-15 | Done
97 | View News Detail | Manage News | Simple | Iteration 1 | CE181988 | Đỗ Đăng Khoa | Iteration 1 | 2025-06-08 | 2025-06-10 | 2025-06-15 | Done
98 | View All Reviews for Dashboard | Manage Reviews | Simple | Iteration 3 | CE180441 | Dương Đinh Thế Vinh | Iteration 3 | 2025-06-17 | 2025-06-29
99 | Update Status Review Detail | Manage Reviews | Simple | Iteration 3 | CE180441 | Dương Đinh Thế Vinh | Iteration 3 | 2025-06-18 | 2025-06-29
102 | View All Amenites | Manage Amenites | Simple | Iteration 1 | CE181640 | Lê Huỳnh Nhựt Khanh | Iteration 1 | 2025-06-09 | 2025-06-12 | 2025-06-12 | Done
103 | View Amenite Detail | Manage Amenites | Simple | Iteration 1 | CE181640 | Lê Huỳnh Nhựt Khanh | Iteration 1 | 2025-06-12 | 2025-06-13 | 2025-06-13 | Done
104 | Delete Amenite | Manage Amenites | Simple | Iteration 1 | CE181640 | Lê Huỳnh Nhựt Khanh | Iteration 1 | 2025-06-15 | 2025-06-16 | 2025-06-16 | Done
105 | Edit Amenite | Manage Amenites | Simple | Iteration 1 | CE181640 | Lê Huỳnh Nhựt Khanh | Iteration 1 | 2025-06-13 | 2025-06-14 | 2025-06-14 | Done
106 | Edit Booking | Manage Bookings | Simple | Iteration 3 | CE180441 | Dương Đinh Thế Vinh | Iteration 3 | 2025-06-17 | 2025-06-29
107 | View Customer Detail | Manage Customer | Simple | Iteration 1 | CE181640 | Lê Huỳnh Nhựt Khanh | Iteration 1 | 2025-09-16 | 2025-09-17 | 2025-09-17 | Done
108 | Edit Customer | Manage Customer | Simple | Iteration 1 | CE181640 | Lê Huỳnh Nhựt Khanh | Iteration 1 | 2025-09-17 | 2025-09-18 | 2025-09-18 | Done
109 | Search Room For Dashboard | Manage Rooms | Simple | Iteration 1 | CE180749 | Kiều Hoàng Mạnh Khang | Iteration 1 | 2025-05-27 | 2025-05-29 | 2025-05-29 | Done
110 | View Confirm Booking | MManager Booking | Simple | Iteration 1 | CE180749 | Kiều Hoàng Mạnh Khang | Iteration 1 | 2025-05-27 | 2025-05-29 | 2025-05-29
111 | [7 empty] | 2025-09-09 | 2025-09-09 | 2025-09-09
112 | [7 empty] | 2025-09-10 | 2025-09-10 | 2025-09-10
113 | [7 empty] | 2025-09-11 | 2025-09-11 | 2025-09-11
114 | [7 empty] | 2025-09-12 | 2025-09-12 | 2025-09-12
115 | [7 empty] | 2025-09-13 | 2025-09-13 | 2025-09-13
116 | [7 empty] | 2025-09-14 | 2025-09-14 | 2025-09-14
117 | [7 empty] | 2025-09-15 | 2025-09-15 | 2025-09-15
118 | [7 empty] | 2025-09-16 | 2025-09-16 | 2025-09-16
119 | [7 empty] | 2025-09-17 | 2025-09-17 | 2025-09-17
120 | [7 empty] | 2025-09-18 | 2025-09-18 | 2025-09-18
121 | [7 empty] | 2025-09-19 | 2025-09-19 | 2025-09-19
122 | [7 empty] | 2025-09-20 | 2025-09-20 | 2025-09-20
123 | [7 empty] | 2025-09-21 | 2025-09-21 | 2025-09-21
124 | [7 empty] | 2025-09-22 | 2025-09-22 | 2025-09-22
125 | [7 empty] | 2025-09-23 | 2025-09-23 | 2025-09-23
126 | [7 empty] | 2025-09-24 | 2025-09-24 | 2025-09-24
127 | [7 empty] | 2025-09-25 | 2025-09-25 | 2025-09-25
128 | [7 empty] | 2025-09-26 | 2025-09-26 | 2025-09-26
129 | [7 empty] | 2025-09-27 | 2025-09-27 | 2025-09-27
130 | [7 empty] | 2025-09-28 | 2025-09-28 | 2025-09-28
131 | [7 empty] | 2025-09-29 | 2025-09-29 | 2025-09-29
132 | [7 empty] | 2025-09-30 | 2025-09-30 | 2025-09-30
133 | [7 empty] | 2025-10-01 | 2025-10-01 | 2025-10-01
134 | [7 empty] | 2025-10-02 | 2025-10-02 | 2025-10-02
135 | [7 empty] | 2025-10-03 | 2025-10-03 | 2025-10-03
136 | [7 empty] | 2025-10-04 | 2025-10-04 | 2025-10-04
137 | [7 empty] | 2025-10-05 | 2025-10-05 | 2025-10-05
138 | [7 empty] | 2025-10-06 | 2025-10-06 | 2025-10-06
139 | [7 empty] | 2025-10-07 | 2025-10-07 | 2025-10-07
140 | [7 empty] | 2025-10-08 | 2025-10-08 | 2025-10-08
141 | [7 empty] | 2025-10-09 | 2025-10-09 | 2025-10-09
142 | [7 empty] | 2025-10-10 | 2025-10-10 | 2025-10-10
143 | [7 empty] | 2025-10-11 | 2025-10-11 | 2025-10-11
144 | [7 empty] | 2025-10-12 | 2025-10-12 | 2025-10-12
145 | [7 empty] | 2025-10-13 | 2025-10-13 | 2025-10-13
146 | [7 empty] | 2025-10-14 | 2025-10-14 | 2025-10-14
147 | [7 empty] | 2025-10-15 | 2025-10-15 | 2025-10-15
148 | [7 empty] | 2025-10-16 | 2025-10-16 | 2025-10-16
149 | [7 empty] | 2025-10-17 | 2025-10-17 | 2025-10-17
150 | [7 empty] | 2025-10-18 | 2025-10-18 | 2025-10-18
151 | [7 empty] | 2025-10-19 | 2025-10-19 | 2025-10-19
152 | [7 empty] | 2025-10-20 | 2025-10-20 | 2025-10-20
153 | [7 empty] | 2025-10-21 | 2025-10-21 | 2025-10-21
154 | [7 empty] | 2025-10-22 | 2025-10-22 | 2025-10-22
155 | [7 empty] | 2025-10-23 | 2025-10-23 | 2025-10-23
156 | [7 empty] | 2025-10-24 | 2025-10-24 | 2025-10-24
157 | [7 empty] | 2025-10-25 | 2025-10-25 | 2025-10-25
158 | [7 empty] | 2025-10-26 | 2025-10-26 | 2025-10-26
159 | [7 empty] | 2025-10-27 | 2025-10-27 | 2025-10-27
160 | [7 empty] | 2025-10-28 | 2025-10-28 | 2025-10-28
161 | [7 empty] | 2025-10-29 | 2025-10-29 | 2025-10-29
162 | [7 empty] | 2025-10-30 | 2025-10-30 | 2025-10-30
163 | [7 empty] | 2025-10-31 | 2025-10-31 | 2025-10-31
164 | [7 empty] | 2025-11-01 | 2025-11-01 | 2025-11-01
165 | [7 empty] | 2025-11-02 | 2025-11-02 | 2025-11-02
166 | [7 empty] | 2025-11-03 | 2025-11-03 | 2025-11-03
167 | [7 empty] | 2025-11-04 | 2025-11-04 | 2025-11-04
168 | [7 empty] | 2025-11-05 | 2025-11-05 | 2025-11-05
169 | [7 empty] | 2025-11-06 | 2025-11-06 | 2025-11-06
170 | [7 empty] | 2025-11-07 | 2025-11-07 | 2025-11-07
171 | [7 empty] | 2025-11-08 | 2025-11-08 | 2025-11-08
172 | [7 empty] | 2025-11-09 | 2025-11-09 | 2025-11-09
173 | [7 empty] | 2025-11-10 | 2025-11-10 | 2025-11-10
174 | [7 empty] | 2025-11-11 | 2025-11-11 | 2025-11-11
175 | [7 empty] | 2025-11-12 | 2025-11-12 | 2025-11-12
176 | [7 empty] | 2025-11-13 | 2025-11-13 | 2025-11-13
177 | [7 empty] | 2025-11-14 | 2025-11-14 | 2025-11-14
178 | [7 empty] | 2025-11-15 | 2025-11-15 | 2025-11-15
179 | [7 empty] | 2025-11-16 | 2025-11-16 | 2025-11-16
180 | [7 empty] | 2025-11-17 | 2025-11-17 | 2025-11-17
181 | [7 empty] | 2025-11-18 | 2025-11-18 | 2025-11-18
182 | [7 empty] | 2025-11-19 | 2025-11-19 | 2025-11-19
183 | [7 empty] | 2025-11-20 | 2025-11-20 | 2025-11-20
184 | [7 empty] | 2025-11-21 | 2025-11-21 | 2025-11-21
185 | [7 empty] | 2025-11-22 | 2025-11-22 | 2025-11-22
186 | [7 empty] | 2025-11-23 | 2025-11-23 | 2025-11-23
187 | [7 empty] | 2025-11-24 | 2025-11-24 | 2025-11-24
188 | [7 empty] | 2025-11-25 | 2025-11-25 | 2025-11-25
189 | [7 empty] | 2025-11-26 | 2025-11-26 | 2025-11-26
190 | [7 empty] | 2025-11-27 | 2025-11-27 | 2025-11-27
191 | [7 empty] | 2025-11-28 | 2025-11-28 | 2025-11-28
192 | [7 empty] | 2025-11-29 | 2025-11-29 | 2025-11-29
193 | [7 empty] | 2025-11-30 | 2025-11-30 | 2025-11-30
194 | [7 empty] | 2025-12-01 | 2025-12-01 | 2025-12-01
195 | [7 empty] | 2025-12-02 | 2025-12-02 | 2025-12-02
196 | [7 empty] | 2025-12-03 | 2025-12-03 | 2025-12-03
197 | [7 empty] | 2025-12-04 | 2025-12-04 | 2025-12-04
198 | [7 empty] | 2025-12-05 | 2025-12-05 | 2025-12-05
199 | [7 empty] | 2025-12-06 | 2025-12-06 | 2025-12-06
200 | [7 empty] | 2025-12-07 | 2025-12-07 | 2025-12-07
201 | [7 empty] | 2025-12-08 | 2025-12-08 | 2025-12-08
202 | [7 empty] | 2025-12-09 | 2025-12-09 | 2025-12-09
203 | [7 empty] | 2025-12-10 | 2025-12-10 | 2025-12-10
204 | [7 empty] | 2025-12-11 | 2025-12-11 | 2025-12-11
205 | [7 empty] | 2025-12-12 | 2025-12-12 | 2025-12-12
206 | [7 empty] | 2025-12-13 | 2025-12-13 | 2025-12-13
207 | [7 empty] | 2025-12-14 | 2025-12-14 | 2025-12-14
208 | [7 empty] | 2025-12-15 | 2025-12-15 | 2025-12-15
209 | [7 empty] | 2025-12-16 | 2025-12-16 | 2025-12-16
210 | [7 empty] | 2025-12-17 | 2025-12-17 | 2025-12-17
211 | [7 empty] | 2025-12-18 | 2025-12-18 | 2025-12-18
212 | [7 empty] | 2025-12-19 | 2025-12-19 | 2025-12-19
213 | [7 empty] | 2025-12-20 | 2025-12-20 | 2025-12-20
214 | [7 empty] | 2025-12-21 | 2025-12-21 | 2025-12-21
215 | [7 empty] | 2025-12-22 | 2025-12-22 | 2025-12-22
216 | [7 empty] | 2025-12-23 | 2025-12-23 | 2025-12-23
217 | [7 empty] | 2025-12-24 | 2025-12-24 | 2025-12-24
218 | [7 empty] | 2025-12-25 | 2025-12-25 | 2025-12-25
219 | [7 empty] | 2025-12-26 | 2025-12-26 | 2025-12-26
220 | [7 empty] | 2025-12-27 | 2025-12-27 | 2025-12-27
221 | [7 empty] | 2025-12-28 | 2025-12-28 | 2025-12-28
222 | [7 empty] | 2025-12-29 | 2025-12-29 | 2025-12-29
223 | [7 empty] | 2025-12-30 | 2025-12-30 | 2025-12-30
224 | [7 empty] | 2025-12-31 | 2025-12-31 | 2025-12-31
225 | [7 empty] | 2026-01-01 | 2026-01-01 | 2026-01-01
226 | [7 empty] | 2026-01-02 | 2026-01-02 | 2026-01-02
227 | [7 empty] | 2026-01-03 | 2026-01-03 | 2026-01-03
228 | [7 empty] | 2026-01-04 | 2026-01-04 | 2026-01-04
229 | [7 empty] | 2026-01-05 | 2026-01-05 | 2026-01-05
230 | [7 empty] | 2026-01-06 | 2026-01-06 | 2026-01-06
231 | [7 empty] | 2026-01-07 | 2026-01-07 | 2026-01-07
232 | [7 empty] | 2026-01-08 | 2026-01-08 | 2026-01-08
233 | [7 empty] | 2026-01-09 | 2026-01-09 | 2026-01-09
234 | [7 empty] | 2026-01-10 | 2026-01-10 | 2026-01-10
235 | [7 empty] | 2026-01-11 | 2026-01-11 | 2026-01-11
236 | [7 empty] | 2026-01-12 | 2026-01-12 | 2026-01-12
237 | [7 empty] | 2026-01-13 | 2026-01-13 | 2026-01-13
238 | [7 empty] | 2026-01-14 | 2026-01-14 | 2026-01-14
239 | [7 empty] | 2026-01-15 | 2026-01-15 | 2026-01-15
240 | [7 empty] | 2026-01-16 | 2026-01-16 | 2026-01-16
241 | [7 empty] | 2026-01-17 | 2026-01-17 | 2026-01-17
242 | [7 empty] | 2026-01-18 | 2026-01-18 | 2026-01-18
243 | [7 empty] | 2026-01-19 | 2026-01-19 | 2026-01-19
244 | [7 empty] | 2026-01-20 | 2026-01-20 | 2026-01-20
245 | [7 empty] | 2026-01-21 | 2026-01-21 | 2026-01-21
246 | [7 empty] | 2026-01-22 | 2026-01-22 | 2026-01-22
247 | [7 empty] | 2026-01-23 | 2026-01-23 | 2026-01-23
248 | [7 empty] | 2026-01-24 | 2026-01-24 | 2026-01-24
249 | [7 empty] | 2026-01-25 | 2026-01-25 | 2026-01-25
250 | [7 empty] | 2026-01-26 | 2026-01-26 | 2026-01-26
251 | [7 empty] | 2026-01-27 | 2026-01-27 | 2026-01-27
252 | [7 empty] | 2026-01-28 | 2026-01-28 | 2026-01-28
253 | [7 empty] | 2026-01-29 | 2026-01-29 | 2026-01-29
254 | [7 empty] | 2026-01-30 | 2026-01-30 | 2026-01-30
255 | [7 empty] | 2026-01-31 | 2026-01-31 | 2026-01-31
256 | [7 empty] | 2026-02-01 | 2026-02-01 | 2026-02-01
257 | [7 empty] | 2026-02-02 | 2026-02-02 | 2026-02-02
258 | [7 empty] | 2026-02-03 | 2026-02-03 | 2026-02-03
259 | [7 empty] | 2026-02-04 | 2026-02-04 | 2026-02-04
260 | [7 empty] | 2026-02-05 | 2026-02-05 | 2026-02-05
261 | [7 empty] | 2026-02-06 | 2026-02-06 | 2026-02-06
262 | [7 empty] | 2026-02-07 | 2026-02-07 | 2026-02-07
263 | [7 empty] | 2026-02-08 | 2026-02-08 | 2026-02-08
264 | [7 empty] | 2026-02-09 | 2026-02-09 | 2026-02-09
265 | [7 empty] | 2026-02-10 | 2026-02-10 | 2026-02-10
266 | [7 empty] | 2026-02-11 | 2026-02-11 | 2026-02-11
267 | [7 empty] | 2026-02-12 | 2026-02-12 | 2026-02-12
268 | [7 empty] | 2026-02-13 | 2026-02-13 | 2026-02-13
269 | [7 empty] | 2026-02-14 | 2026-02-14 | 2026-02-14
270 | [7 empty] | 2026-02-15 | 2026-02-15 | 2026-02-15
271 | [7 empty] | 2026-02-16 | 2026-02-16 | 2026-02-16
272 | [7 empty] | 2026-02-17 | 2026-02-17 | 2026-02-17
273 | [7 empty] | 2026-02-18 | 2026-02-18 | 2026-02-18
274 | [7 empty] | 2026-02-19 | 2026-02-19 | 2026-02-19
275 | [7 empty] | 2026-02-20 | 2026-02-20 | 2026-02-20
276 | [7 empty] | 2026-02-21 | 2026-02-21 | 2026-02-21
277 | [7 empty] | 2026-02-22 | 2026-02-22 | 2026-02-22
278 | [7 empty] | 2026-02-23 | 2026-02-23 | 2026-02-23
279 | [7 empty] | 2026-02-24 | 2026-02-24 | 2026-02-24
280 | [7 empty] | 2026-02-25 | 2026-02-25 | 2026-02-25
281 | [7 empty] | 2026-02-26 | 2026-02-26 | 2026-02-26
282 | [7 empty] | 2026-02-27 | 2026-02-27 | 2026-02-27
283 | [7 empty] | 2026-02-28 | 2026-02-28 | 2026-02-28
284 | [7 empty] | 2026-03-01 | 2026-03-01 | 2026-03-01
285 | [7 empty] | 2026-03-02 | 2026-03-02 | 2026-03-02
286 | [7 empty] | 2026-03-03 | 2026-03-03 | 2026-03-03
287 | [7 empty] | 2026-03-04 | 2026-03-04 | 2026-03-04
288 | [7 empty] | 2026-03-05 | 2026-03-05 | 2026-03-05
289 | [7 empty] | 2026-03-06 | 2026-03-06 | 2026-03-06
290 | [7 empty] | 2026-03-07 | 2026-03-07 | 2026-03-07
291 | [7 empty] | 2026-03-08 | 2026-03-08 | 2026-03-08
292 | [7 empty] | 2026-03-09 | 2026-03-09 | 2026-03-09
293 | [7 empty] | 2026-03-10 | 2026-03-10 | 2026-03-10
294 | [7 empty] | 2026-03-11 | 2026-03-11 | 2026-03-11
295 | [7 empty] | 2026-03-12 | 2026-03-12 | 2026-03-12
296 | [7 empty] | 2026-03-13 | 2026-03-13 | 2026-03-13
297 | [7 empty] | 2026-03-14 | 2026-03-14 | 2026-03-14
298 | [7 empty] | 2026-03-15 | 2026-03-15 | 2026-03-15
299 | [7 empty] | 2026-03-16 | 2026-03-16 | 2026-03-16
300 | [7 empty] | 2026-03-17 | 2026-03-17 | 2026-03-17
301 | [7 empty] | 2026-03-18 | 2026-03-18 | 2026-03-18
302 | [7 empty] | 2026-03-19 | 2026-03-19 | 2026-03-19
303 | [7 empty] | 2026-03-20 | 2026-03-20 | 2026-03-20
304 | [7 empty] | 2026-03-21 | 2026-03-21 | 2026-03-21
305 | [7 empty] | 2026-03-22 | 2026-03-22 | 2026-03-22
306 | [7 empty] | 2026-03-23 | 2026-03-23 | 2026-03-23
307 | [7 empty] | 2026-03-24 | 2026-03-24 | 2026-03-24
308 | [7 empty] | 2026-03-25 | 2026-03-25 | 2026-03-25
309 | [7 empty] | 2026-03-26 | 2026-03-26 | 2026-03-26
310 | [7 empty] | 2026-03-27 | 2026-03-27 | 2026-03-27
311 | [7 empty] | 2026-03-28 | 2026-03-28 | 2026-03-28
312 | [7 empty] | 2026-03-29 | 2026-03-29 | 2026-03-29
313 | [7 empty] | 2026-03-30 | 2026-03-30 | 2026-03-30
314 | [7 empty] | 2026-03-31 | 2026-03-31 | 2026-03-31
315 | [7 empty] | 2026-04-01 | 2026-04-01 | 2026-04-01
316 | [7 empty] | 2026-04-02 | 2026-04-02 | 2026-04-02
317 | [7 empty] | 2026-04-03 | 2026-04-03 | 2026-04-03
318 | [7 empty] | 2026-04-04 | 2026-04-04 | 2026-04-04
319 | [7 empty] | 2026-04-05 | 2026-04-05 | 2026-04-05
320 | [7 empty] | 2026-04-06 | 2026-04-06 | 2026-04-06
321 | [7 empty] | 2026-04-07 | 2026-04-07 | 2026-04-07
322 | [7 empty] | 2026-04-08 | 2026-04-08 | 2026-04-08
323 | [7 empty] | 2026-04-09 | 2026-04-09 | 2026-04-09
324 | [7 empty] | 2026-04-10 | 2026-04-10 | 2026-04-10
325 | [7 empty] | 2026-04-11 | 2026-04-11 | 2026-04-11
326 | [7 empty] | 2026-04-12 | 2026-04-12 | 2026-04-12
327 | [7 empty] | 2026-04-13 | 2026-04-13 | 2026-04-13
328 | [7 empty] | 2026-04-14 | 2026-04-14 | 2026-04-14
329 | [7 empty] | 2026-04-15 | 2026-04-15 | 2026-04-15
330 | [7 empty] | 2026-04-16 | 2026-04-16 | 2026-04-16
331 | [7 empty] | 2026-04-17 | 2026-04-17 | 2026-04-17
332 | [7 empty] | 2026-04-18 | 2026-04-18 | 2026-04-18
333 | [7 empty] | 2026-04-19 | 2026-04-19 | 2026-04-19
334 | [7 empty] | 2026-04-20 | 2026-04-20 | 2026-04-20
335 | [7 empty] | 2026-04-21 | 2026-04-21 | 2026-04-21
336 | [7 empty] | 2026-04-22 | 2026-04-22 | 2026-04-22
337 | [7 empty] | 2026-04-23 | 2026-04-23 | 2026-04-23
338 | [7 empty] | 2026-04-24 | 2026-04-24 | 2026-04-24
339 | [7 empty] | 2026-04-25 | 2026-04-25 | 2026-04-25
340 | [7 empty] | 2026-04-26 | 2026-04-26 | 2026-04-26
341 | [7 empty] | 2026-04-27 | 2026-04-27 | 2026-04-27
342 | [7 empty] | 2026-04-28 | 2026-04-28 | 2026-04-28
343 | [7 empty] | 2026-04-29 | 2026-04-29 | 2026-04-29
344 | [7 empty] | 2026-04-30 | 2026-04-30 | 2026-04-30
345 | [7 empty] | 2026-05-01 | 2026-05-01 | 2026-05-01
346 | [7 empty] | 2026-05-02 | 2026-05-02 | 2026-05-02
347 | [7 empty] | 2026-05-03 | 2026-05-03 | 2026-05-03
348 | [7 empty] | 2026-05-04 | 2026-05-04 | 2026-05-04
349 | [7 empty] | 2026-05-05 | 2026-05-05 | 2026-05-05
350 | [7 empty] | 2026-05-06 | 2026-05-06 | 2026-05-06
351 | [7 empty] | 2026-05-07 | 2026-05-07 | 2026-05-07
352 | [7 empty] | 2026-05-08 | 2026-05-08 | 2026-05-08
353 | [7 empty] | 2026-05-09 | 2026-05-09 | 2026-05-09
354 | [7 empty] | 2026-05-10 | 2026-05-10 | 2026-05-10
355 | [7 empty] | 2026-05-11 | 2026-05-11 | 2026-05-11
356 | [7 empty] | 2026-05-12 | 2026-05-12 | 2026-05-12
357 | [7 empty] | 2026-05-13 | 2026-05-13 | 2026-05-13
358 | [7 empty] | 2026-05-14 | 2026-05-14 | 2026-05-14
359 | [7 empty] | 2026-05-15 | 2026-05-15 | 2026-05-15
360 | [7 empty] | 2026-05-16 | 2026-05-16 | 2026-05-16
361 | [7 empty] | 2026-05-17 | 2026-05-17 | 2026-05-17
362 | [7 empty] | 2026-05-18 | 2026-05-18 | 2026-05-18
363 | [7 empty] | 2026-05-19 | 2026-05-19 | 2026-05-19
364 | [7 empty] | 2026-05-20 | 2026-05-20 | 2026-05-20
365 | [7 empty] | 2026-05-21 | 2026-05-21 | 2026-05-21
366 | [7 empty] | 2026-05-22 | 2026-05-22 | 2026-05-22
367 | [7 empty] | 2026-05-23 | 2026-05-23 | 2026-05-23
368 | [7 empty] | 2026-05-24 | 2026-05-24 | 2026-05-24
369 | [7 empty] | 2026-05-25 | 2026-05-25 | 2026-05-25
370 | [7 empty] | 2026-05-26 | 2026-05-26 | 2026-05-26
371 | [7 empty] | 2026-05-27 | 2026-05-27 | 2026-05-27
372 | [7 empty] | 2026-05-28 | 2026-05-28 | 2026-05-28
373 | [7 empty] | 2026-05-29 | 2026-05-29 | 2026-05-29
374 | [7 empty] | 2026-05-30 | 2026-05-30 | 2026-05-30
375 | [7 empty] | 2026-05-31 | 2026-05-31 | 2026-05-31
376 | [7 empty] | 2026-06-01 | 2026-06-01 | 2026-06-01
377 | [7 empty] | 2026-06-02 | 2026-06-02 | 2026-06-02
378 | [7 empty] | 2026-06-03 | 2026-06-03 | 2026-06-03
379 | [7 empty] | 2026-06-04 | 2026-06-04 | 2026-06-04
380 | [7 empty] | 2026-06-05 | 2026-06-05 | 2026-06-05
381 | [7 empty] | 2026-06-06 | 2026-06-06 | 2026-06-06
382 | [7 empty] | 2026-06-07 | 2026-06-07 | 2026-06-07
383 | [7 empty] | 2026-06-08 | 2026-06-08 | 2026-06-08
384 | [7 empty] | 2026-06-09 | 2026-06-09 | 2026-06-09
385 | [7 empty] | 2026-06-10 | 2026-06-10 | 2026-06-10
386 | [7 empty] | 2026-06-11 | 2026-06-11 | 2026-06-11
387 | [7 empty] | 2026-06-12 | 2026-06-12 | 2026-06-12
388 | [7 empty] | 2026-06-13 | 2026-06-13 | 2026-06-13
389 | [7 empty] | 2026-06-14 | 2026-06-14 | 2026-06-14
390 | [7 empty] | 2026-06-15 | 2026-06-15 | 2026-06-15
391 | [7 empty] | 2026-06-16 | 2026-06-16 | 2026-06-16
392 | [7 empty] | 2026-06-17 | 2026-06-17 | 2026-06-17
393 | [7 empty] | 2026-06-18 | 2026-06-18 | 2026-06-18
394 | [7 empty] | 2026-06-19 | 2026-06-19 | 2026-06-19
395 | [7 empty] | 2026-06-20 | 2026-06-20 | 2026-06-20
396 | [7 empty] | 2026-06-21 | 2026-06-21 | 2026-06-21
397 | [7 empty] | 2026-06-22 | 2026-06-22 | 2026-06-22
398 | [7 empty] | 2026-06-23 | 2026-06-23 | 2026-06-23
399 | [7 empty] | 2026-06-24 | 2026-06-24 | 2026-06-24
400 | [7 empty] | 2026-06-25 | 2026-06-25 | 2026-06-25